## LoF
List of Findings
Checking					Review Meeting and Rework
No.	Review Object	Location of Finding	Finding Descripion	Input from	Severity		Status
1	Sch	General	Output impedance of ADC Digital Output is high, I suggest you leave the level translator as close as possible to the ADC. 0.2*3.3V/(1mA~2mA) = 330~660R		Major	I choose CONFIG3 OUT_DRV 1 mA. / Close to the ADC to reduce capacity? / I wanted to have distance from uP and Translator. Lets discuss.
2	Sch	General	Output impedance of level translator is around 58R (0,7V/0,012A=58,33R). I suggest you control the impedance of the trace to 60R, and left a 0R resistor in case is needed later to the signal reflection if it exists.		Major	I do not understand the effect of how the noise enters the ADC. / I placed some resistors and capacitors so I can play with values.
3	Layout		Due to the high impedance of the ADC, and low impedance of the Leveltranslator, place the level translator as close as possible to the ADC.		Major	Lets discuss.
4	Layout	General	Change the stackup to 4 layers. This will allow to control the impedance of the traces and have a better GND plane.		Major	Lets discuss. By adding layers I increase capacity, more current spikes. / I don’t know.
5	Layout	SPI	Route the SPI communication traces on IN2, with solid GND on IN1 and Bottom of this traces to avoid crosstalking. Also add Vias as guard for this traces.		Major	Lets discuss.
6	Layout		Move C33 to the right side of the opamp U202, connecting first the C33 to power supply and after to the IC. Like it was done on the U201		Minor	Done.
7	Layout		Missing decoupling capacitors on IC’s U206, U208, U209, U210 and U212, U214 on both sides.		Major	Done, wow, I fortot! Thanks.
8	Sch	General	I understand your concern about noise of the uC and the Analog circutis. But I propose and experiment here, unify the ground between digital and analog on the board. Do the measurement, after the measurements with the solid ground cut with a dremmel the board to separated both ground like you have now and measure it again. Do a line on the top silkscreen to guide the cut like this:		Minor	I connected the gnd planes by soldering bridges and / could not see an influence. But good Idea to connect and later on separate. / Lets discuss.
9	Sch	rp2350	Control the impedance of the tracks between Rpi and Flash. It’s not so important because they are very close, but it’s a good approach to use.		Minor
10	Sch	rp2350	Was used 4 GPIO's in parallel, and the relay connected to the Rpi GPIO consumes 140mW, which is around 42mA. According to the Chapter 9.6 Output drive strength can be set to 2mA, 4mA, 8mA or 12mA. So you need to ensure the correct port configuration or simple use a SOT23 mosfet like Si2312BDS to turn ON the relay.		Major	It’s a bistable relais. Bistable to avoid heat. / I need to apply voltage in both directions. / According to IV curves of the Rpi datasheet it should be absolutely sufficient / with standard 4mA outputs. / 20250407a_berechnungen.ods / Idea of relais: Relais is switched of at power outage. C201 remains charged.
11	Sch	rp2350	Add freewheel diode on the relay coil		Major	As I keep the outputs as outputs I do not expect voltage spikes. / I added freeweel diodes anyway.
12	Sch	USB	Power supply can provide max 1W. I think the power will be lower but I did not check each component. Rpi seems to be around 50mW, relay 140mW.		Minor	I measured 0.2A at the USB port, seams to be ok.
13	Sch	USB	Add a fuse like 1210L110/16 in series with the USB 5V.		Minor	ok
14	Sch	USB	Add a TVS like SMBJ5.0CA on the 5V of the USB, to avoid a wild USB voltage damage the board.		Minor	ok
15	Layout	General	When you finish the layout you can use a Plugin to add via stitching of GND on the PCB. Unfortunatelly the Plugin I will recommend has a Bug on Kicad 9 and was not fixed yet. So the procedure of this issue need to be done https://github.com/jsreynaud/kicad-action-scripts/issues/81		Minor	Cool, didn’t know
16	Sch	Root	I saw 100nF decoupling caps 0402 on the rpi, and 1uF/10uF 0805. Usually we use 100nF in 0603 for easy soldering compare to 0402 everywhere.		Minor	I agree.
17	Sch		The input filter is set to 178.7 kHz. Is this low enough for removing you expected alias? Since it is a sigma-delta ADC, could be enough.		Minor	The sigma delta clock ist 25 MHz. fmod = 6.25 Mhz. Nyquist 3.12 MHz. / Should be ok.
18	Layout		Move the 22 Ohm resistors that pertain to the outputs closer to their respective IC: / CLK, START, SDI, CS and RESET should be moved closer to the microcontroller side. / DRDY, SDO should be moved closer to the ADC. / This should be in general applied to any high-speed-ish digital signal: add the series resistor as close to the output as possible.		Minor	A now added a resistor to the input and output.
19	Sch		Move this symbol to the micro controller page.		Minor
20	Sch		There is an effort to split the grounds, but then the DGND from the ADC is not connected to a digital GND. In general, I’m in favor of using a single ground, like Fabio suggested.		Major	Thoughts: Datasheet 9.4.1: they recommend a single gnd on the pcb. Bonding wires have impedance inside the ADC. Multiple gnd pins therefore help even though I connect them to the same gnd plane outside.
22	Sch		It seems 5V from the USB are boosted to 9V by a Murata DCDC isolated module. This 9V are then feed to OPA4990 to generate the 7V used in the analog supply. Is the PSRR of these opamps high enough?		Major	I
23	Sch		Jitter can have a significant impact on the noise performance of high resolution ADCs. It may be worth to check the ADC’s clock jitter. / (I believe you use the external OSC, but both notes are very telling) / 7.3.3.1 Internal Oscillator: / The internal oscillator is not available for the maximum-speed mode. Because of the clock jitter of / the internal oscillator, only use the internal oscillator for dc signal measurements. The internal oscillator is not / recommended when measuring ac signals. / Maybe the microcontroller or the level translator worsens the jitter. / 7.3.3.2 External Clock / Clock jitter results in timing variations when the signal is sampled, leading to degraded SNR performance. A / low-jitter clock is essential to meet data sheet SNR performance. / https://www.analog.com/media/en/reference-design-documentation/design-notes/dn1013f.pdf		Major	I take a pwm output of the RP2350: 25 MHz. It is derived from the XTAL. / No idea about the jitter. / I used a FlipFlop to synchronize SLCK to CLK. This helped.
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66